## Sheet1
Estimated by: BROWN | [5 empty] | Sheet 2__ of 2__ Date: 6/14/2008
Checked by: GREENE | [5 empty] | Date: 6/23/2008
EQUIPMENT ESTIMATE
Project Number: GM07-803 |  |  |  |  | Project Title: CONSTRUCT BUILDING 101
Unit: NMCB FOUR |  |  |  |  | Project Location: U.S. NAVAL MAGAZINE
Construction Activity Number and Description: 31 20 EARTH MOVING
Note: The initial requirement from page one must now be refined to accomplish a work schedule. Refinement of this estimate will also increase efficiency of equipment so it will be utilized close to full capacity. The work schedule requires completion of fill in an 18-day period. The weather at the project area is researched and an assumption is made that 3 days in every 17 working days will be lost due to rain. Therefore, 15 working days would be available for work. (7)
36,000 CYD = 2,400 CYD per day (The amount that must be hauled daily to complete the work on schedule)
15 working days Task requirement: 2,400 CYD of earth fill will be hauled each day 2,400 CYD per day = 3 (This is three times the output of loading and hauling spread shown on page 1)
800 CYD hauled per 8 - hour day
Revised equipment requirement: (required to load and haul per a 15-day schedule)
Three |  | Front-end loaders (2 1/2 CYD capacity)
One Bulldozer (to maintain borrow pit)
One |  | Grader (to maintain haul road)
15 |  | Dump trucks (10 CYD capacity) (Recommend one or two extra trucks be added to assure that a truck will always be waiting to be loaded so that the front-end loader will work at full capacity or during breakdowns.)
2,400 CYD per day |  |  | = 2 pieces of compacting equipment required.
1,200 CYD per day work rate
2,400 CYD per day |  |  |  | = 2 pieces of spreading equipment required
1,400 CYD per day work rate
| Two | Bulldozers (to spread earth fill)
| One | Water distributor truck (for moisture control)
| One | Rubber-tired wobbly wheel roller (on standby for compaction and sealing fill when rain is expected) (can be towed by above bulldozer or tractor).
Note: This refined estimate takes the work period from 45 days down to 15 days; one-third less time. Production has been tripled but equipment has not, with equipment working at or as close to capacity as possible.