## Sheet1
Work Element Description | Unit | Man-hours per Unit
02 41 19.23 B-1
Selective Demolition, Rubbish Handling
(0010) Chute, circular, prefabricated steel, 18-inch diameter | LF | 0.798
(0020) 30-inch diameter | LF | 1.064
(0030) Dust partition, 6 mil polyethylene, 2- by 4-inch frame (two builders) | SF | 1.064
(0040) Rubbish disposal up to 5 miles | CYD | 1.500
02 41 19.27
Selective Demolition, Torch Cutting
(0010) Steel, 1-inch-thick plate | LF | 0.030
(0020) 1-inch-diameter bar | Each | 0.050
Oxygen lance cutting, reinforced concrete walls, (0030) 12- to 16-inch-thick walls | LF | 1.064
Crew sizes are dictated by safety, scope of the project, weight, and bulk of materiels handled.
Notes: 1. Work includes removal of item and stacking or piling onsite for removal at ground level. 2. Second floor or upper story work includes dumping into rubbish chutes. 3. Concrete demolition is figured on using pneumatic tools with average crew of two tool operators and three to five laborers. 4. Work includes salvage of materiels (e.g., cleaning and pulling nails).