## Sheet1
Work Element Description | Unit | Man-hours per Unit
03 30 53.10
Mixing Concrete
Hand mixing onsite:
(0010) two boards or boats | CYD | 3.20
Machine mixing onsite:
(0020) 16 CF capacity | CYD | 1.60
(0030) 11 CF capacity | CYD | 2.70
Tailor to 1 CF of capacity
Transit mix truck (8 CYD capacity) | CYD | 0.56
Minimum suggested crew size: Refer to the following notes.
Notes: 1. This data provides information needed to compute the time required to survey a parcel or to perform the layout for a construction project. 2. Hand mixing using two boards eliminates waiting for a batch to be mixed before dry charging the mixing board, as the mixers alternate boards. With twelve men, the maximum output is about 8 CYD per day. 3. Warm weather (90 to 100 degrees) will slow mixing time and add 0.5 man-hours per CYD. 4. Labor to charge a mixer can be reduced by the use of a small front-end loader, but at least one man must remain on each aggregate stock pile to monitor bucket loading. 5. Transit mix man-hours are based on using four trucks, average haul of five miles, and four men operating a dry cement batching plant. 6. Large job man-day estimates are dependent on equipment used, as well as manufacturer’s ratings and recommendations.