## Sheet1
Work Element Description | Unit | Direct from Chute | Wheeled | Pumped | Crane and Bucket
03 31 05.70 Placing Concrete
Lintel or sill, 8 x 8, Cast in place, including forming | LF | * | (0005) 0.5 | * | *
Beams, elevated | CYD | * | * | (0010) 1.60 | (0020) 2.40
Columns, square or round |  | * | * | (0030) 1.60 | (0040) 2.70 (0060) 1.963
12 inches thick | CYD
18 inches thick | CYD |  |  | (0050) 1.066
24 inches thick | CYD |  |  | (0070) 1.044 | (0080) 1.543
Elevated slabs |  | * | *
less than 6 inches thick | CYD |  |  | (0090) 0.685 | (0100) 1.137
6 to 10 inches thick | CYD |  |  | (0110) 0.60 | (0120) 0.982
Footings, continuous
Shallow | CYD | (0130) 0.600 |  | (0140) 0.641 | (0150) 1.200
deep | CYD | (0160) 0.514 | * | (0170) 0.600 | (0180) 0.982
Footings, spread
under 1 CYD | CYD | (0190) 1.309 |  | (0200) 1.477 | (0210) 2.400
over 5 CYDs | CYD | (0220) 0.600 |  | (0230) 0.641 | (0240) 1.080
Grade beams | CYD | (0250) 0.480 | * | (0260) 0.536 | (0270) 0.900
Pile caps | CYD | (0280) 0.800 | * | (0290) 0.873 | (0300) 1.359
Slabs on grade up to 6 inches thick over 6 inches thick |  |  | *
| CYD | (0310) 0.654 | (0320) 0.738 | (0330) 0.983
| CYD | (0340) 0.436 |  | (0350) 0.520 | (0360) 0.750
Walls |  |  | *
8 inches thick | CYD | (0370) 0.800 |  | (0380) 0.960 | (0390) 1.350
12 inches thick | CYD | (0400) 0.720 |  | (0410) 0.873 | (0420) 1.200
1 inch thick | CYD | (0430) 0.700 |  | (0440) 0.800 | (0450) 1.137
Wheeled concrete dumping, add to placing time above, walking cart
up to 50-foot haul, add | CYD | * | (0460) 0.422 | * | *
up to 150-foot haul, add | CYD |  | (0470) 0.563
up to 250-foot haul, add | CYD |  | (0480) 0.750
Minimum suggested crew size: one crew leader, two skilled and six unskilled laborers, and two equipment operators.
Notes: 1. This figure provides man-hours for labor and equipment to place and vibrate concrete. 2. For upper stories, add per story: placed by pump, use a 1.07 multiplier; placed by bucket or crane, use a 1.05 multiplier. 3. Construction that moves in and out of ramps, runways, or staging is not included. For moving and in and out, use 0.22 man-hours per linear foot. 4. Major considerations in planning concrete placement are: method of placement, accessibility, rate of placement in regard to form design, amount and frequency of delivery governed by the ability to screed, tamp, and finish.